## Projects
Name | Status | Phase | Type | Start Date | End Date | Department | Plant | Sponsor | Cost Center | Est. Hours | Act. Hours
Tool Availability Tracking project | Ongoing | PreProcess | NewProject | 2026-05-03 | - | Continuous Improvement | AUT N96 | Hafsa Mislah | - | - | -
AI HR CHATBOT | Ongoing | Pipeline | NewProject | 2026-05-05 23:00 | - | - | AUT N96 | - | - | - | -
IMS | Ongoing | Monitoring | NewProject | 2026-01-01 23:00 | 2026-02-16 | - | AUT N96 | - | - | - | 255
EHS E-Dojo PH3 | Done | Closing | NewPhase | 2026-02-14 23:00 | 2026-04-12 23:00 | EHS | AUT N96 | - | - | 500 | 172
Digital Twins Smart Factory | Ongoing | Pipeline | NewProject | 2026-05-05 08:41 | - | - | AUT N96 | - | - | - | -
PE Project | Ongoing | Pipeline | NewProject | 2026-03-12 | - | PE | AUT N96 | - | - | - | -
COO Phase 2 | Ongoing | Pipeline | NewPhase | 2026-04-26 23:00 | - | GLOG | AUT N96 | - | - | - | -
PM SAP for Laboratory | Ongoing | Pipeline | NewProject | 2026-04-22 23:00 | - | Laboratory | AUT N96 | - | - | - | -
Set up_SOLAR HARNESS FG | Ongoing | Pipeline | NewProject | 2026-04-14 23:00 | - | - | AUT N96 | - | - | - | -
Connectivity Technologies Profiling pahse 2 | Ongoing | Pipeline | NewPhase | 2026-03-31 14:23 | - | - | AUT N96 | - | - | - | -
Manual/Pro format | Ongoing | Pipeline | NewProject | 2026-02-25 | - | - | AUT N96 | - | - | 200 | -
PE- E-Drawing Phase 3 | Ongoing | Execution | NewPhase | 2026-03-11 10:57 | - | - | AUT N96 | - | - | - | -
CAPEX | Ongoing | Pipeline | NewProject | 2026-03-03 11:49 | - | Procurement | AUT N96 | - | - | - | -
Portail Social | Ongoing | Pipeline | NewProject | 2026-03-03 09:53 | - | - | AUT N96 | ilham bachisse | 1195589 | - | -
Tracker Action System | Ongoing | Pipeline | NewProject | 2026-02-27 | - | - | AUT N96 | - | - | - | -
Lab Genius PH2 | Ongoing | Pipeline | NewPhase | 2026-02-25 | - | Laboratory | AUT N96 | - | - | - | -
Automated KPIs | Ongoing | Execution | NewProject | 2026-01-29 14:20 | - | - | AUT N96 | Hdid, Mohammed / Benlamkaddem, Mouncif | - | - | -
Checklist | Ongoing | Execution | NewProject | 2026-01-29 14:19 | - | - | AUT N96 | - | - | - | -
D-PIM | Ongoing | Execution | NewProject | 2026-01-29 14:18 | - | - | AUT N96 | - | - | - | -
D-SPC (L3) | Ongoing | Execution | NewProject | 2026-01-29 14:17 | - | - | AUT N96 | Benlamkaddem, Mouncif / Hdid, Mohammed | - | - | -
D-QCPC (L2) | Ongoing | Execution | NewProject | 2026-01-29 14:17 | - | - | AUT N96 | Benlamkaddem, Mouncif | - | - | -
Visit Flow PH2 | Ongoing | PreProcess | NewPhase | 2026-01-28 | - | - | AUT N96 | - | - | - | -
OPEX Tool Spare | Ongoing | PreProcess | NewProject | 2026-01-27 | - | - | AUT N96 | EL Amrani Zacaria | - | - | -
DSI (Digital Sorting Interface) | Ongoing | Execution | NewProject | 2026-01-28 23:00 | - | - | AUT N96 | Ahmed El Ammari | - | - | -
Digitalization of Mold Improvement & Manufacturing Follow Up Tracking | Ongoing | Pipeline | NewProject | 2026-01-26 23:00 | - | MOLDING | AUT N96 | Gouyez Benallal, Osama | - | - | -
incomplete box | OnHold | Pipeline | NewProject | 2026-01-26 08:53 | - | - | AUT N96 | Kennoun, Adnane | - | - | -
pps tm2 stamping | Ongoing | Pipeline | NewProject | 2026-01-26 08:51 | 2026-02-25 | - | AUT N96 | - | - | - | -
DSPC | Ongoing | Pipeline | NewProject | 2026-01-26 08:49 | - | - | AUT N96 | - | - | - | -
DPIM | Ongoing | Pipeline | NewProject | 2026-01-26 08:47 | - | - | AUT N96 | - | - | - | -
DF | Ongoing | Execution | NewProject | 2026-01-26 08:45 | - | - | AUT N96 | - | - | - | -
DTM | Ongoing | Execution | NewProject | 2026-01-23 10:53 | - | - | AUT N96 | - | - | - | -
MCTV | Ongoing | Execution | NewProject | 2026-01-23 10:51 | - | - | AUT N96 | - | - | - | -
Andon | Ongoing | Execution | NewProject | 2026-01-23 10:50 | - | - | AUT N96 | - | - | - | -
Machine Connectivity L2 Molding | Ongoing | Execution | NewProject | 2026-01-21 09:03 | - | - | AUT N96 | - | - | - | -
DTO for ICT wave2 | Ongoing | PreProcess | NewPhase | 2025-12-23 09:21 | - | - | AUT N96 | - | - | - | -
Sourcing Phase 3 AI | Ongoing | Planification | NewPhase | 2025-11-28 23:00 | 2026-05-10 23:00 | - | AUT N96 | - | 1195700 | 900 | -
Connectivity Technologies Profiling | Ongoing | Execution | NewProject | 2025-11-30 23:00 | 2026-02-12 23:00 | IT | AUT N96 | - | - | 540 | -
cost to serve platform | Ongoing | Execution | NewProject | 2025-12-16 14:05 | - | - | AUT N96 | - | - | - | -
CS Coverage File | Ongoing | PreProcess | NewProject | 2025-12-16 13:52 | - | - | AUT N96 | - | - | - | -
Mfg. Cost Estimation | Ongoing | Initiation | NewProject | 2025-12-16 13:31 | - | - | AUT N96 | - | - | 252 | -
Inventory / Planning | Ongoing | PreProcess | NewProject | 2025-12-16 13:20 | - | - | AUT N96 | - | - | - | -
Breaks management | Ongoing | Pipeline | NewProject | 2025-12-16 13:19 | - | - | AUT N96 | - | - | - | -
Space design process | Ongoing | PreProcess | NewProject | 2025-12-16 13:18 | - | - | AUT N96 | - | - | - | -
Manufacturing Dashboard TFZ | OnHold | Pipeline | NewProject | 2025-12-15 11:47 | - | - | AUT N96 | - | - | - | -
Manufacturing Dashboard TAC1 | Done | Closing | NewProject | 2025-12-22 | 2026-01-08 | - | AUT N96 | - | - | - | -
Digital Twin Process Control | OnHold | Execution | NewProject | 2025-12-15 11:42 | - | - | AUT N96 | - | - | - | -
Digital Archive extention to aut PH2 | Done | Closing | Extension | 2025-03-01 | 2025-04-30 | - | AUT N96 | - | - | - | -
Digital Archive extention to aut | Done | Closing | NewProject | 2023-08-01 | 2023-09-30 | - | AUT N96 | - | - | 170 | 150
Digital Twin Saftey PH1 | Done | Closing | NewProject | 2025-02-17 | 2025-07-15 | - | AUT N96 | - | - | - | -
MCTV CA Phase 2 | OnHold | Monitoring | Sustain | 2025-12-15 09:43 | - | Production | AUT N96 | - | - | - | -
IT Asset Management | Done | Closing | NewProject | 2025-02-24 | 2025-08-30 | - | AUT N96 | - | - | - | -
MTS Enhancements | OnHold | Monitoring | NewProject | 2025-03-01 | 2025-08-29 23:00 | Warehouse | AUT N96 | - | - | - | -
Good Idea V3 | Ongoing | Closing | NewProject | 2025-03-10 | 2025-11-10 | - | AUT N96 | - | - | - | -
Integrated MOC Platform for EHS Compliance | Ongoing | PreProcess | NewProject | 2025-12-10 | - | EHS | AUT N96 | Najoua Abouidate | - | 190 | -
Gemba: Digital Reporting & Tracking of Unsafe Conditions and Unsafe Behaviors | Ongoing | PreProcess | NewProject | 2025-12-10 | - | - | AUT N96 | Najoua Abouidate | - | - | -
ICT MR Molding PH1 | Done | Closing | NewProject | 2025-06-27 | 2025-06-14 | - | AUT N96 | - | - | - | -
EHS E- Dojo PH2 | Done | Closing | NewPhase | 2025-12-04 | 2026-01-29 | EHS | AUT N96 | Najoua Abouidate | 1195911 | 1000 | 980
EHS E- Dojo Molding | Done | Closing | NewProject | 2025-05-27 | 2025-06-14 | - | AUT N96 | - | - | - | -
PE- E-Drawing Phase 2 | Done | Execution | NewProject | 2024-03-01 | 2025-12-09 | Engineering | AUT N96 | - | - | 280 | 300
DTM TM2 | Done | Closing | Sustain | 2025-12-09 09:33 | 2025-03-12 | Tooling | AUT N96 | - | - | - | -
Andon TM2 | Done | Closing | Sustain | 2025-12-09 09:30 | 2025-03-15 | Maintenance | AUT N96 | - | - | - | -
DQIP TM2 | Done | Closing | Sustain | 2025-12-09 09:06 | 2025-03-15 | Quality | AUT N96 | - | - | - | -
Digital Academy | Ongoing | Execution | NewProject | 2025-12-09 08:23 | - | DC | AUT N96 | - | - | 550 | -
Scaning Convoyor | Ongoing | Execution | NewProject | 2025-06-17 | - | - | AUT N96 | - | - | - | -
Strategic Souring Phase 2 | Ongoing | Execution | NewProject | 2025-03-03 | 2025-06-12 | - | AUT N96 | - | - | - | -
CARPOOL | Done | Closing | NewProject | 2025-12-01 | 2025-12-08 | - | AUT N96 | - | - | 150 | 122
Tracebility Mate/Gem NET | Ongoing | Monitoring | NewProject | 2025-12-08 15:24 | - | Production | AUT N96 | - | - | - | -
Sample Shop Process Optimization | Ongoing | Monitoring | NewProject | 2025-03-03 | - | - | AUT N96 | - | - | - | -
Revenue Dashboard for CS | Done | Closing | NewProject | 2025-10-29 | 2025-12-30 | - | AUT N96 | - | - | - | -
Manufacturing Dashboard Toubkal | Done | Closing | NewProject | 2025-08-02 23:00 | 2026-01-20 23:00 | - | AUT N96 | - | - | 600 | -
CS Ordering Optimization Phase 2 | Done | Execution | NewProject | 2025-04-07 | 2025-11-27 | CSR | AUT N96 | - | - | 288 | 168
Tableland traceability | Ongoing | Execution | NewProject | 2025-06-02 | - | - | AUT N96 | - | - | - | -
E-Mobility Traceability | Done | Closing | NewProject | 2025-12-08 14:00 | - | - | AUT N96 | - | - | - | -
CSR-REFTRACK | Done | Closing | NewProject | 2025-11-21 | 2025-12-03 | CSR | AUT N96 | - | - | 120 | 84
Maintenance Data Traceability & Performance Dashboard | Ongoing | PreProcess | NewProject | 2025-10-29 | - | Maintenance | AUT N96 | Benhineuch Mohammed / Maintenance Department | 1249 | - | -
Guarding Management System (GMS) | Ongoing | PreProcess | NewProject | 2025-11-26 23:00 | - | Maintenance | AUT N96 | Faysal Rahimi / GFS | 1195592 | 500 | -
HR Medical Management | Ongoing | Pipeline | NewProject | 2025-12-08 13:20 | - | Human Resources | AUT N96 | - | - | - | -
HR Business Support Complaints Management | Ongoing | PreProcess | NewProject | 2025-10-23 23:00 | - | Human Resources | AUT N96 | - | - | - | -
Transport Smart Assignment & Management | Ongoing | Initiation | NewProject | 2025-10-22 23:00 | - | Human Resources | AUT N96 | - | - | - | -
Canteen Management System | Ongoing | PreProcess | NewProject | 2025-10-24 | - | - | AUT N96 | Lghoul Rachid | - | - | -
HR Items Shop | Ongoing | PreProcess | NewProject | 2025-10-24 | - | Human Resources | AUT N96 | - | - | - | -
Intern Tracking | Ongoing | PreProcess | NewProject | 2025-10-24 | - | Human Resources | AUT N96 | Lghoul Rachid | - | - | -
Digital Archive extention to ICT | OnHold | Pipeline | NewProject | 2025-12-08 13:06 | - | - | AUT N96 | - | - | - | -
DTO For ICT wave1 | Done | Closing | NewProject | 2025-03-11 | 2025-12-12 | Engineering | AUT N96 | Azzedine Salhi | 1195761 | 250 | 238
Ordering Optimization - TECO Enhancements | OnHold | Closing | NewProject | 2025-12-04 14:58 | - | Production | AUT N96 | - | - | - | -
ABM Phase 1 | Done | Closing | NewProject | 2025-09-27 23:00 | 2026-03-16 | Sales | AUT N96 | - | - | 400 | 382
Lab Genius PH1 : Chemical Test Enhancements | Ongoing | Initiation | NewProject | 2025-12-30 | 2026-02-10 | Laboratory | AUT N96 | - | - | - | -
MCA Digital Academy & Skill Matrix | Done | Closing | NewProject | 2025-02-24 | 2025-09-15 | Prod/HR/QUALITY | AUT N96 | - | - | - | -
Digital Audit System( LPA, Saftey inspection, Quality…) | Ongoing | PreProcess | NewProject | 2025-02-24 | 2025-06-27 23:00 | TEQA/EHS | AUT N96 | - | - | - | -
Ford G74 Project | OnHold | Execution | NewProject | 2025-12-04 14:04 | - | Process | AUT N96 | - | - | - | -
Blocked Stock management | Done | Monitoring | NewProject | 2025-03-01 | 2025-08-29 23:00 | Supply Chain | AUT N96 | - | - | - | -
QRM Enhancements | Ongoing | Execution | NewProject | 2025-11-25 08:41 | - | Quality | AUT N96 | - | - | - | -
Manufacturing Dashboard IND enhancments | Ongoing | Execution | NewProject | 2025-01-30 23:00 | - | - | AUT N96 | - | - | - | -
COO-Country of origin PH1 | Done | Closing | NewProject | 2025-07-31 | 2026-01-30 | - | AUT N96 | - | - | 600 | 573
Sustaining | Ongoing | Execution | NewProject | 2025-09-28 23:00 | - | - | AUT N96 | - | - | 206 | -
IT PORTAL | OnHold | Execution | NewProject | 2025-09-27 23:00 | - | - | AUT N96 | - | - | - | -
Measure Diciplinary Enhancements | Done | Closing | NewProject | 2025-10-16 | 2026-01-26 | - | AUT N96 | - | - | 174 | 200
Fill Study Application | Ongoing | Pipeline | NewProject | 2025-11-19 09:55 | - | - | AUT N96 | - | - | - | -
Digital Quality Control | 6 | Pipeline | NewProject | 2025-11-19 09:53 | - | - | AUT N96 | - | - | - | -
Program Management | Done | Monitoring | NewProject | 2025-11-19 09:48 | - | - | AUT N96 | - | - | - | -
Visa Management | Done | Closing | NewProject | 2025-03-03 | 2025-09-01 | - | AUT N96 | - | - | - | -
Supply chain Dashboard ICT | Done | Closing | NewProject | 2025-03-01 | 2025-09-24 | - | AUT N96 | - | - | 832 | 1232
EHS GLobal Platform | Done | Closing | NewProject | 2025-03-01 | 2025-09-30 23:00 | IT | AUT N96 | Khadija | 9000 | 900 | 1300
EHS Training Tracking APP | Done | Closing | NewProject | 2025-03-01 | 2025-10-06 23:00 | IT | AUT N96 | khadija | 900 | 1000 | 1600